## Customer Facing Timeline
IMPLEMENTATION TIMELINE
ACCOUNT MANAGER |  | Name |  |  | COMPANY NAME |  | Name
LAUNCH DATE |  | Date |  |  | PROJECT PARTNER |  | Name
PHASE | TITLE |  | TOPIC | ITEM | INFORMATION |  |  |  |  | BY-WHEN
[5 empty] | Details | Resource(s) |  | Notes | Status | Owner | Others Involved | Due Date | Time
1 | Introductions & Discovery |  | Handoff | Kickoff call |  |  |  |  | In progress |  |  |  | 1 hour
|  |  | Goals | Align on objectives and KPIs |  |  |  |  | In progress |  |  |  | 30 mins
|  |  | Project Plan | Outline project timeline |  |  |  |  | In progress |  |  |  | n/a
2 | Zipline Configuration |  | Site Build | Site URL |  |  |  |  | Not started |  |  |  | 1 hour
|  |  |  | Primary brand color |  |  |  |  | Not started
|  |  |  | Digest name | Subject line - example: daily scrub |  |  |  | Not started
|  |  |  | Digest sender name | From name - example: Retail Communications |  |  |  | Not started
|  |  |  | Digest banner |  |  |  |  | Not started
|  |  |  | Message categories | Typical is 5-7 |  |  |  | Not started
|  |  |  | Quick links |  |  |  |  | Not started
|  |  |  | Security Levels |  |  |  |  | Not started
|  |  |  | Beginning of week |  |  |  |  | Not started
|  |  |  | Policy copy |  |  |  |  | Not started
|  |  |  | Policy frequency |  |  |  |  | Not started
|  |  |  | Distribution lists |  |  |  |  | Not started
|  |  |  | Drag and drop format | Word/Google docs |  |  |  | Not started
|  |  | IT | Login format |  |  |  |  | Not started |  |  |  | 2 hours
|  |  |  | Hierarchy file & distribution list attributes |  |  |  |  | Not started
|  |  |  | User file |  |  |  |  | Not started
|  |  |  | SSO configuration |  |  |  |  | Not started
|  |  |  | Safelisting |  |  |  |  | Not started
|  |  | Message Publishing | Users with publisher_create |  |  |  |  | Not started |  |  |  | 1 hour
|  |  |  | Users with publisher_notify |  |  |  |  | Not started
|  |  |  | Business Partner Publishing Status | On/off |  |  |  | Not started
|  |  |  | Users with Business Partner Publishing permission |  |  |  |  | Not started
|  |  | Field Publishing | Feature status |  |  |  |  | Not started |  |  |  | 30 mins
|  |  |  | Users |  |  |  |  | Not started
|  |  |  | Category |  |  |  |  | Not started
|  |  |  | Message priority |  |  |  |  | Not started
|  |  | Groups | Feature status |  |  |  |  | Not started |  |  |  | 30 mins
|  |  |  | Direct messaging status |  |  |  |  | Not started
|  |  |  | Enable users to direct message HQ |  |  |  |  | Not started
|  |  |  | Show employee numbers in invite employee list |  |  |  |  | Not started
|  |  |  | Users with group creation permission |  |  |  |  | Not started
|  |  |  | Auto-subscribe groups and attribute rules | Example: all users in store 6 will be auto-subscribed to store 6 |  |  |  | Not started
|  |  |  | Pre-loaded groups |  |  |  |  | Not started
|  |  | Survey | Feature status |  |  |  |  | Not started |  |  |  | 30 mins
|  |  |  | Users with Survey permission |  |  |  |  | Not started
|  |  | Resource Library | Feature status |  |  |  |  | Not started |  |  |  | 30 mins
|  |  |  | Users with Library admin permission |  |  |  |  | Not started
|  |  |  | Library banner |  |  |  |  | Not started
|  |  |  | Topic titles |  |  |  |  | Not started
|  |  |  | Topic icons |  |  |  |  | Not started
|  |  |  | Setup mode |  |  |  |  | Not started
|  |  |  | ZipTips folder |  |  |  |  | Not started
|  |  |  | Resource migration |  |  |  |  | Not started |  |  |  | 2 hours
3 | Publisher Training |  | Self-learning | Send self-learning resources |  |  |  |  | Not started |  |  |  | 2 hours
|  |  |  | Team to jot down specific questions and examples |  |  |  |  | Not started
|  |  | In-person/Virtual Training Session | Platform overview |  |  |  |  | Not started |  |  |  | 15 mins
|  |  |  | Publishing |  |  |  |  | Not started |  |  |  | 30 mins
|  |  |  | Survey |  |  |  |  | Not started |  |  |  | 30 mins
|  |  |  | Resource Library |  |  |  |  | Not started |  |  |  | 30 mins
|  |  |  | Field view |  |  |  |  | Not started |  |  |  | 30 mins
|  |  |  | Groups |  |  |  |  | Not started |  |  |  | 30 mins
|  |  | Drop-in/Question Session | [5 empty] | Not started |  |  |  | 1 hour
Not started
4 | Launch Plan |  | Upperfield Plan | [5 empty] | Not started |  |  |  | 1 hour
Not started
Not started
Not started
|  |  | Stores Plan | [5 empty] | Not started |  |  |  | 1 hour
Not started
Not started
Not started
|  |  | HQ Plan (optional) | [5 empty] | Not started |  |  |  | 30 mins
Not started
|  |  | Prepoluate Content in Zipline | [5 empty] | Not started |  |  |  | 4 hours
Not started
5 | Field Training |  | Upperfield | [5 empty] | Not started |  |  |  | 2 hours
Not started
Not started
Not started
|  |  | Stores | [5 empty] | Not started |  |  |  | 2 hours
Not started
Not started
Not started
|  |  | HQ (optional) | [5 empty] | Not started |  |  |  | 30 mins
Not started
6 | Launch |  | Socialization | Upload welcome message |  |  |  |  | Not started |  |  |  | n/a
|  |  |  | Upload generic intro video |  |  |  |  | Not started |  |  |  | n/a
|  |  | Launch | Pat yourself on the back - congrats! |  |  |  |  | Not started |  |  |  | n/a
7 | Post-launch |  | Performance & Adoption | Turn on reporting |  |  |  |  | Not started |  |  |  | n/a
|  |  |  | Demo and train on reporting |  |  |  |  | Not started |  |  |  | n/a
|  |  | Learnings | Discuss learnings |  |  |  |  | Not started |  |  |  | n/a
|  |  |  | Make adjustments as needed |  |  |  |  | Not started |  |  |  | n/a
|  |  | Account Management | Continue monitoring performance |  |  |  |  | Not started |  |  |  | n/a
|  |  |  | Schedule ongoing touchbases |  |  |  |  | Not started |  |  |  | n/a

## Sample Timeline Gantt
TIMELINE OVERVIEW |  | TIMELINE
[13 empty] | UF Pilot Go Live |  | Pilot Go Live | [12 empty] | Chain Roll out
| Key Milestones | May 15th | May 22nd | July Wk 3 | July Wk 4 | July Wk 5 | Aug Wk 1 | Aug wk 2 | Aug wk 3 | Aug Wk 4 | Sept Wk 1 | Sept Wk 2 | Sept Wk 3 | Sept Wk 4 | Sept Wk 5 | Oct wk 1 | Oct wk 2 | Oct Wk 3 | Oct wk 4 | Nov wk 1 | Nov wk 2 | Nov wk 3 | Nov wk 4 | Dec wk 1 | Dec wk 2 | Dec wk 3 | Dec wk 4 | Dec wk 5 | Jan wk 1 | Jan wk 2 | Jan wk 3 | Jan wk 4 | Feb Wk 1
Discovery | Discovery (Stores, DC, HR/L & D)
Configuration | IT Configurations
UI Customizations
Permissioning
Resource Library Design
Comms Strategy | Overarching content strategy
Content Mapping
Business Alignment
| Template Creation |  |  | TBD- Based on based on Business Partner Publishing
Add Zipline Info
Publisher Training | Web Training
Office Hours
Content Build | Back Publish Comms
Migrate Content to the RL
Launch Plan | UF Training Alignment/Content Review
DC's Training Alignment/Content Review
Stores Training Alignment/Content Review
Launch Marketing
Field Training | UF Alignment Call/ Training
Office Hours | bar: Oct wk 1
DC Alignment Call/ Training
Office Hours | bar: Oct wk 1
Stores Alignment Call/ Training
Office Hours | bar: Oct wk 1
Launch | Welcome Email
Welcome Video
Post Launch | Share reporting & Post Launch insights | bar: Oct wk 1 to Oct Wk 3
Conduct Office Hours
Weekly TB- Discuss learnings
Chain Roll Out | Review Pilot Learnings | bar: Nov wk 4 to Dec wk 1
Align on any outstanding integrations | bar: Dec wk 2 to Dec wk 3
Build the roll out plan/training | bar: Dec wk 2 to Dec wk 3
Build out the roadmap for any Additional Features not turned on during pilot/chain roll out

## Rollout + Training Timeline
ROLLOUT TIMELINE
| Key Milestones | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
HQ | Business Partner Announcement Email + Video
Busines Partner Training Call
HQ Pre-Launch Announcement Email + Video
HQ Launch Day Announcement
Upper Field | UF Pre-Launch Announcement Email + Video
Pre-Launch Survey
UF Launch Day Announcement Email + Video
UF Launch Day Zipline Comm
UF Training + Rollout Call
UF Drop in Hours
UF Zip Tips
UF Post Launch Survey
Stores | Stores Pre-Launch Announcement Email + Video
Stores Pre-Llaunch Survey
Stores Launch Day Announcement Email + Video
Stores Launch Day Zipline Comm
Stores Training + Rollout Call
Stores Drop in Hours
Stores Zip Tips
Stores Post Launch Survey
ROLLOUT DELIVERABLES
Resources | BP + HQ Emails
UF Emails
Store Emails
| Zipline Launch Comm | Week 1: Link
| UF Launch Call Script | Week 1: Link
| UF Training Guide | Week 1: Link
| Stores Launch Call Script | Week 1: Link
| Stores Training Guide | Week 1: Link
Resource Library Training Pages
| Zip Tips | Week 1: Link; Week 2: *this link is for our GDrive folder
| Zip Tip Videos | Week 1: Link; Week 2: *this link is for our Video Tutorial library
| Launch Video | Week 1: Link; Week 2: No Library; Week 3: No Groups
| Pre + Post Launch Surveys | Week 1: Pre; Week 2: Post; Week 3: *both links to the left are live Google Docs

## Security Level Mapping
JOB TITLE a/o CODE | ZIPLINE SECURITY LEVEL | Zipline Team Type
SR VP OPS & SALES | HQ | HQ
VP DEPARTMENT | HQ
SR REGIONAL MANAGER | Region Leader | Region
REGIONAL MANAGER | Region Leader
DISTRICT MANAGER | District Leader | District
DISTRICT MANAGER IN TRAINING | District Leader
STORE MANAGER | Manager | Store
STORE MANAGER - HOURLY | Manager
ASSISTANT STORE MANAGER | Store Leadership Team | Store
DEPARTMENT MANAGER | Store Leadership Team
DEPARTMENT LEADER | Store Leadership Team
PART TIME ASSOCIATE | Associate | Store
FULL TIME ASSOCIATE | Associate
DEPT SPECIALIST | Associate